## Sheet1
TIP / WBS No. | Description | Let Date | Completion Date | Status | Construction Cost | Contractor | Project Administrator | Comments
Projects Under Construction
17BP.9.R.61 (C203681) | EXPRESS DESIGN BUILD - Replace (2) Bridges in Davidson, (1) in Davie, (3) Bridges in Rowan, and (4) Bridges in Stokes County. | 2015-05-19 | Estimated June 1, 2020 | 87.6% Complete Design and construction in progress | 10642621 | Smith-Rowe, LLC | Larry Shaver (336)249-6255 | Express Design Build Contract - Contract consist of replacement of 11 bridges throughout the Division. Contract includes - Br. #258 over Swearing Creek on SR 1272, and Br. #410 over Leonard Creek on SR 1844 in Davidson Co; (1) bridge in Davie Co; (3) bridges in Rowan Co; and (5) bridges in Stokes Co. Work has been completed on Ollie Harkie Road in Davie Co., Barringer Street in Rowan Co., Scercy Road in Rowan Co.,Bradshaw Rd. in Rowan Co.,Snow Hill Church Rd in Stokes Co., Dan George Rd. in Stokes Co., Tom Shelton Rd. in Stokes Co., Jersey Church Rd in Davidson County and these roads have been reopened to traffic. The new bridge on Dodgetown road has been completed and traffic is in its final pattern. Removal of the existing structure has been completed. Minor grading operations are ongoing, this will be followed by final paving. The Dodgetown Rd project is tenatively scheduled to be complete April 2020. Old Greensboro Rd. in Davidson County was closed down on July 8, 2019 the Contractor has completed relocating the existing waterlines. Demolition of the existing bridge has been completed. Contractor is currently constructing the new bridge substructure. Project site scheduled to be completed by June 2020. All road closures will have signed off-site detours. | DAVIDSON DAVIE ROWAN STOKES | Darren Trantham
17BP.9.R.104 (Old B-5784) (C203681 SA) | EXPRESS DESIGN BUILD Supplemental Agreement - Replace Bridge #125 over North Double Creek on SR 1484 (Dan George Rd) in Stokes County. | 2018-05-04 |  |  | 943196 |  |  |  | STOKES | Darren Trantham
2020CPT.09.03.10301 2020CPT.09.04.20301 (DI00218) | Contract Resurfacing of (3) Sections of Primary Routes and (13) Sections of Secondary Routes in Davie County, totalling 17.367 miles | Nov. 28, 2018 | Revised March 1, 2020 | 42.3% Complete | 3851014 | APAC-Atlantic, Inc. | Jeremy Guy, PE (336)747-7900 | The contractor paved all but two of the maps on this contract. Maps 1 & 2 will be scheduled for Spring 2020. | DAVIE | Jeremy Guy
2020CPT.09.12.20302 (DI00208) | Asphalt Surface Treatment (AST) of (20) sections of various Secondary routes in Davie County, totalling 30.64 miles | Oct. 10, 2018 | Revised March 1, 2020 | 12% Complete | 808067 | Whitehurst Paving Co Inc | Jeremy Guy, PE (336)747-7900 | Maps 1 & 8 are complete and the rest of the contract will begin in Spring 2020. | DAVIE | Jeremy Guy
Projects Under Construction
I-0911A 34147.3.4 (C203965) | DESIGN BUILD - Grading (Widening), Drainage, Paving and ITS on I-40 from West of NC 801 in Davie Co. to SR 1101 (Harper Rd) in Forsyth Co. (2.614 miles) | 2017-07-18 | Revised Jan. 19, 2021 | 60% Complete | 71962779 | Flatiron Constructors, Inc/Blythe Development Co - JV | Jordan Scott, PE (336)293-9610 | DESIGN BUILD - Project will widen approximately 3.3 miles of I-40 to a six-lane divided facility from west of NC 801 in Davie County to east of SR 1101 (Harper Road/Tanglewood Park Business Road) in Forsyth County. The project will replace dual bridges on I-40 over the Yadkin River and accommodate a future greenway by replacing the Bert’s Way roadway bridge over I-40 with a pedestrian bridge. All noise walls were approved for construction. Phase II traffic shift has been completed. Bridge demo on EB structure underway. Widen and stablization work ongoing around 801 interchange. Pedestrain bridge erection Fall of 2020. Sound wall construction near complete in I-40WB direction. Sound wall on I-40EB to begin Spring 2020. | DAVIE FORSYTH | Barry Byrd
I-5823 50466.3.1 (C204241) | Pavement Rehabilitation on I-40 from W. of US 601 to the Iredell County line in Davie Co. | Jan. 15, 2019 | Revised July 6, 2022 (vegetation established by Jan. 2, 2023) | 47% Complete | 55641354 | Flatiron Constructors Inc | Jeremy Guy, PE (336)747-7900 | The contractor has completed most of the shoulder widening and crossover work throughout the project. Almost all of the concrete patching repairs on the project have also been completed. The contractor has shifted the Westbound traffic over to the Eastbound lanes therefore both East and West bound traffic is in a one lane, head to head pattern from Mile Marker 162 to 168. While traffic is shifted, the contractor is in the process of removing and replacing the existing structure on I-40 over Hunting Creek. The contractor is also paving, installing guardrail, and building fill sections while they are in this traffic pattern. The traffic is scheduled to stay in this pattern until November 2020. | DAVIE | Jeremy Guy
47793 | Construction of a Roundabout at the I-40 East Bound Ramp Terminal at SR 1410 (Farmington Road) in Davie County | Summer 2018 | TBD | Under construction | 820000 | State Forces | Robert McMath, PE (336)936-6100 | Lighting has been installed. Additional design for a slip right, to be installed. | DAVIE | Scott Jones (DDC)
Projects Under Development
B-5766 45722.3.1 | Replace Bridge #82 over the Dan River on SR 1674 (Sheppard Mill Rd.) in Stokes County | Feb. 28, 2024 | TBD | ROW Acquisition July 29, 2022 | 5125000 | TBD | Daniel Dagenhart (919)747-7800 | * Schedule based on Approved 2020-2029 STIP - DPOC - The new alignment for the bridge replacement will require a lengthy consultation process with State Parks and US National Park Service; schedule has been delayed to reflect this. *The PE work for this project has been temporarily suspended.* | STOKES | Daniel Dagenhart
B-5768 45724.3.1 | Replace Bridge #38 over Cedar Creek on NC 801 in Davie County | Oct. 17, 2023 | TBD | ROW Acquisition Oct. 21, 2022 | 1150000 | TBD | Daniel Dagenhart (336)747-7800 | * Schedule based on Draft 2020-2029 STIP - DPOC - scoped in February, 2019. *The PE work for this project has been temporarily suspended.* | DAVIE | Daniel Dagenhart
BR-0047 49078.3.1 C204394 | Replace Bridge #10 over US 52 on SR 1105 (Meadowbrook Drive) in Stokes County | 2020-06-16 | TBD | ROW Acquisition in progress | 6400000 | TBD | Kevin Fischer, PE (919)707-6514 | Raleigh Let - Planning and Design in process. | STOKES | Daniel Dagenhart
BR-0102 67102.3.1 | Replace Bridge #37 over Big Creek on NC 268 Stokes County | Jan. 1, 2023 | TBD | ROW Acquisition Jan. 1, 2022 | 3200000 | TBD | Kevin Fischer, PE (919)707-6514 | Raleigh Let - New - in Development. *The PE work for this project has been temporarily suspended.* | STOKES | Daniel Dagenhart
EB-5958 48434.3.1 | Blue Heron Trail, from Twins Way (near intersection with US 158) West to the Pedestrian Tunnel, under I-40 in Bermuda Run | 2020-05-29 | TBD |  |  |  |  | Non-DOT Let - Town of Bermuda Run
I-6003 47957.3.1 | Pavement rehabilitation on I-40 from SR 1436 (Pinebrook School Rd) to West of NC 801 in Davie County | Oct. 26, 2022 | TBD |  | 2900000 | TBD | Brett Abernathy, PE (336)747-7800 | * Schedule based on the Approved 2020-2029 STIP - previously I-3600 | DAVIE
R-5736 50194.3.1 | Widen to Multi-lanes - US 601 from SR 1345 (Blaise Church Rd) to SR 1408 (Cana Rd) in Davie County. | 2024-04-16 | TBD | ROW Acquisition April 15, 2022 | 13100000 | TBD | Brett Abernathy, PE (336)747-7800 | * Schedule based on Approved 2020-2029 STIP - Division Design Raleigh Let (DDRL) - Utility coordination is underway. Design is ongoing - hydraulic design is complete and utility coord is nearing completion. *The PE work for this project has been temporarily suspended.* | DAVIE | Connie James
R-5768 44670.3.1 | Upgrade intersection and improve railroad crossing at US 311 and NC 65 in Walnut Cove in Stokes Co. | Oct. 27, 2021 | TBD | ROW Acquisition in progress | 3550000 | TBD | Brett Abernathy, PE (336)747-7800 | * Schedule based on Approved 2020-2029 STIP - Design ongoing. | STOKES | Connie James
R-5789F 44919.3.7 R-5789G 44919.3.8 | ADA Ramps at Various Locations in Davidson, Davie, Forsyth and Rowan Counties | Oct. 27, 2021 | TBD |  | 2900000 | TBD | Brett Abernathy, PE (336)747-7800 | *Schedule based on Approved 2020-2029 STIP - Division POC Let (DPOC) - ON HOLD | Dvdsn, Davie, Forsyth, Rowan | Jeff Turner
R-5828 47100.3.1 | Construct Roundabout at the intersection of US 311 (S. Main Street) and First Street in Walnut Cove in Stokes Co | Jan. 27, 2021 | TBD | ROW in progress Utility relocation to begin soon | 1450000 | TBD | Brett Abernathy, PE (336)747-7800 | * Schedule based on Approved 2020-2029 STIP - DPOC | STOKES | Connie James
R-5854 47542.3.1 | Construct Roundabouts on SR 1410 (Farmington Rd) at I-40 Eastbound Ramp and US 158 intersection in Davie Co | 2024-06-26 | TBD | ROW Acquisition June 30, 2023 | 2200000 | TBD | Brett Abernathy, PE (336)747-7800 | * Schedule based on the Approved 2020-2029 STIP - Planning and design underway for roundabout at Farmington and US 158. Utility Coordination is nearing completion and right of way plans could be finalized in the next couple of months. *The PE work for this project has been temporarily suspended.* | DAVIE | Connie James
Projects Under Development
U-6002 47137.3.1 | Construct Roundabout at intersection of Yadkinville Road (NS) and Wilkesboro Street (NS) in Davie County | 2021-06-23 | TBD | ROW Acquisition in progress | 650000 | TBD | Brett Abernathy, PE (336)747-7800 | * Schedule based on the Approved 2020-2029 STIP - Design in progress. Right of way being acquired. As soon as all ROW is acquired, utility relocation work will begin. ROW acquisition is ON HOLD. | DAVIE | Connie James
U-6187 48647.3.1 | Construct new route 2-Lane Extension of SR 1630 (Baltimore Road) and Interchange at I-40 in Davie County | 2024-03-19 | TBD | ROW Acquisition Aug. 31, 2022 | 30102000 | TBD | Brett Abernathy, PE (336)747-7801 | * Schedule based on the Approved 2020-2029 STIP - New project added, based on results of P5.0. Project has been removed from the suspension list. We are revisiting the scope of work and will be finalizing the scope and estimate over the next month. Survey work is underway. | DAVIE | Connie James
17BP.9.C.12 | Replace pipe #290 on Danbury Creek at SR 1128 (Brown Rd) in Stokes County | Jan. 25, 2023 | TBD | ROW Acquisition July 27, 2022 | 700000 | TBD | Daniel Dagenhart (336)747-7801 | Division Let - Planning and Design in progress | STOKES | Daniel Dagenhart
17BP.9.R.72 | Replace Bridge #8 over Dan River on NC 704 in Stokes County. | Dec. 9, 2020 | TBD | ROW Acquisition June 9, 2020 | 3150000 | TBD | Daniel Dagenhart (336)747-7800 | Division Let - Planning and design is underway. Schedule may change due to environmental issues | STOKES | Daniel Dagenhart
17BP.9.R.83 | Replace Bridge #286 over Little Yadkin River on SR 1236 (Old US 52) in Stokes County | Nov. 16, 2022 | TBD | ROW Acquisition May 16, 2022 | 1400000 | TBD | Daniel Dagenhart (336)747-7800 | Division Let - Planning and Design in progress (25% plans received) | STOKES | Daniel Dagenhart
17BP.9.R.88 | Replace Bridge #76 over Dan River on SR 1432 (Collinstown Rd.) in Stokes County | June 26, 2024 | TBD | ROW Acquisition Jan. 26, 2024 | 2500000 | TBD | Daniel Dagenhart (336)747-7800 | Division Let Planning and design is underway. | STOKES | Daniel Dagenhart
17BP.9.R.93 | Replace Bridge #25 over Bailey Creek on SR 1621 (Beauchamp Rd) in Davie County | Oct. 16, 2024 | TBD | ROW Acquisition April 16, 2024 | 700000 | TBD | Daniel Dagenhart (336)747-7800 | Division Let - project has been scoped | DAVIE | Daniel Dagenhart
17BP.9.R.94 | Replace Bridge #65 over Bear Creek on SR 1313 (Duke Whitaker Rd) in Davie County | 2024-04-10 | TBD | ROW Acquisition Oct. 10, 2023 | 725000 | TBD | Daniel Dagenhart (336)747-7800 | Division Let - project has been scoped | DAVIE | Daniel Dagenhart
17BP.9.R.98 | Replace Bridge #15 over Vade Mecum Creek on NC 66 in Stokes County | Aug. 17, 2022 | TBD | ROW Acquisition Feb. 17, 2021 | 825000 | TBD | Daniel Dagenhart (336)747-7800 | Division Let - Planning and Design in progress (65% plans received) | STOKES | Daniel Dagenhart
17BP.9.R.100 (Old B-4819) | Replace Bridge #105 over Snow Creek on SR 1697 (Pitzer Rd.) in Stokes County | Sept. 23, 2021 | TBD | ROW Acquisition complete | 1600000 | TBD | Daniel Dagenhart (336)747-7800 | Division Let - Planning and Design is complete, - Division Managed and funded by the Division Managed Bridge Program. | STOKES | Daniel Dagenhart
47801 | Re-construct intersection of SR 2019 (Flat Shoals Rd) and NC 8 and add turn lanes in Stokes County | TBD | TBD | in development | 715000 | State Forces | Brett Abernathy, PE (336)747-7800 | High Impact Low Cost | STOKES | Al Blanton
47880 | Construct left turn lanes at intersection of NC 66 and SR 1122 (Mountain View Rd) in Stokes County | TBD | TBD | in development | 250000 | TBD | Brett Abernathy, PE (336)747-7800 | High Impact Low Cost | STOKES | Al Blanton
48462 | Install pedestrian safety improvements including curb & gutter, drainage improvements, ADA wheel chair ramps, fand our rapid flashing beacons on NC 8/89 in Danbury | TBD | TBD | in development | 212000 | TBD | Brett Abernathy, PE (336)747-7801 | High Impact Low Cost | STOKES | Al Blanton
48787 | Construct roundabout at the I-40 Westbound ramp terminal at SR 1410 (Farmington Rd) in Davie County | Aug., 2020 | TBD | in development | 1001000 | State Forces | Brett Abernathy, PE (336)747-7800 | High Impact Low Cost | DAVIE | Al Blanton
49701 | Construct a right turn lane on SR 1800 (Eaton Rd) in Mocksville | TBD | TBD | in development | TBD | State Forces | Brett Abernathy, PE (336)747-7800 | High Impact Low Cost - improvement needed to accomocdate the new Brakebush Processing Plant. Approved but not yet funded | DAVIE | Al Blanton
Completed Projects
17BP.9.R.73 (C204004) | EXPRESS DESIGN BUILD - Replace (3) Bridges in Davidson Co and (2) Bridges in Davie Co | 2017-06-20 | Estimated Completion August 25, 2019 | 99.8% Complete | 6817750 | RE Burns & Sons, Inc | Kelly Seitz, PE (704)630-3220 | Express Design Build Contract - Bridges 82 and 31 are currently waiting 80% vegetation establishment (delayed due to drought conditions). | DAVIDSON DAVIE | Richard Ho
2020CPT.09.09.10851 2020CPT.09.10.20851 (DI00219) | Contract Resurfacing of (5) Sections of Primary Routes and (4) Sections of Secondary Routes in Stokes County, totalling 42.550 miles | Nov. 28, 2018 | Aug. 21, 2019 | 100% Complete | 4725602 | APAC-Atlantic, Inc. | Jeremy Guy, PE (336)747-7900 | Contract is completed and accepted. | STOKES
2020CPT.09.15.20852 (DI00211) | Asphalt Surface Treatment (AST) of (69) sections of various Secondary routes in Stokes County, totalling 55.83 miles | Oct. 10, 2018 | Actual Oct. 23, 2019 | 100% Complete | 1538127 | Whitehurst Paving Co Inc | Jeremy Guy, PE (336)747-7900 | Project was completed Oct. 23, 2019. | STOKES | Thomas Scott
15BPR.18 (C204215) | Bridge Preservation of Bridge #63 on US 64 at Yadkin River in Davie County | Oct. 16, 2018 | Aug. 6, 2019 | 100% Complete | 1262066 | American Civil Constructors, West Coast LLC | Jeremy Guy, PE (336)747-7900 | The contractor has completed all the work on the project. Project accepted August 6, 2019. | DAVIE
R-5789D 44919.3.5 | Install ADA (Americans with Disabilities Act) ramps, curb & gutter, and sidewalks at various locations in Davidson, Davie, and Rowan Counties | Aug. 26, 2019 | 2020-03-17 |  | 281891 | Little Mountain Builders of Catawba County, Inc. | Mezak Tucker, PE (704)630-3200 | Project complete and accepted March 17, 2020 | DAVIDSON DAVIE ROWAN
R-5789E 44919.3.6 (DI00230) |  |  |  | 100% Complete | [5 empty] | Josh Miller
W-5709I 44855.3.9 (DI00223) | Wideline Thermoplastic Pavement Markings on Various Secondary Routes in Davie and Stokes Counties, totalling 73.84 miles | Mar. 27, 2019 | Sept. 30, 2019 | 100% Complete | 2491297 | Ogelsby Construction Co., Inc | JP Couch, PE (336)747-7800 | Work began May 13, 2019. Work was completed on Sept. 30, 2019. | DAVIE STOKES | JP Couch